## Gantt Chart
IS4T702 MSc Project — Gantt Chart (Project Plan)
Student: Faisal Aleem ¦ Supervisor: Janusz ¦ University of South Wales ¦ June 9 - September 11, 2026
Task | June |  |  | July |  |  |  | August |  |  |  |  | September
Week | W1 9-15 Jun | W2 16-22 Jun | W3 23-29 Jun | W4 30 Jun-6 Jul | W5 7-13 Jul | W6 14-20 Jul | W7 21-27 Jul | W8 28 Jul-3 Aug | W9 4-10 Aug | W10 11-17 Aug | W11 18-24 Aug | W12 25-31 Aug | W13 1-7 Sep | W14 8-11 Sep
PROJECT FOUNDATION
✓ Ethics form and first meeting | W1
✓ Literature review (Chapter 2)
EXPERIMENTAL DESIGN
Experimental design and protocol
Python environment and dataset setup |  |  | W3
PROTOTYPE DEVELOPMENT
Baseline classifier implementation
Preprocessing techniques
In-processing techniques
Postprocessing techniques | [6 empty] | W7
EXPERIMENTATION
UCI Adult Income dataset experiments
COMPAS dataset experiments
ANALYSIS AND EVALUATION
Statistical analysis
Fairness metric comparison
Results visualisation | [9 empty] | W10
DISSERTATION WRITING
Chapter 3: Methodology
Chapter 4: Implementation
Chapter 5: Results and Analysis
Chapter 6 and 7: Discussion/Conclusion
Chapter 1: Introduction | [11 empty] | W12
FINALISATION
Proofreading and revision | [12 empty] | W13
Final formatting | [12 empty] | W13
Submission (23:59 deadline) | [13 empty] | W14
KEY MILESTONES
| ✔ M1 Ethics approved | ✔ M2 Literature review done |  | ◆ M3 Design finalised |  |  | ◆ M4 Prototype complete |  | ◆ M5 Experiments complete |  | ◆ M6 Analysis complete | ◆ M7 First draft to supervisor |  | ◆ M8 FINAL SUBMISSION
LEGEND
Project Foundation |  | Experimental Design |  | Prototype Development |  | Experimentation |  | Analysis and Evaluation |  | Dissertation Writing |  | Finalisation |  | Completed task
Notes: Dissertation submission deadline is the second Thursday in September 2026 (September 11, 23:59). Weeks 1-2 tasks are already complete. Total project duration: 14 weeks.

## Task List
# | Phase | Task | Start Date | Start Week | Duration (wks) | Status
1 | Project Foundation | Ethics form and first meeting | 09 Jun 2026 | Week 1 | 1 | Complete
2 | Project Foundation | Literature review (Chapter 2) | 09 Jun 2026 | Week 1 | 2 | Complete
3 | Experimental Design | Experimental design and protocol | 23 Jun 2026 | Week 3 | 2 | Pending
4 | Experimental Design | Python environment and dataset setup | 23 Jun 2026 | Week 3 | 1 | Pending
5 | Prototype Development | Baseline classifier implementation | 30 Jun 2026 | Week 4 | 2 | Pending
6 | Prototype Development | Preprocessing techniques | 07 Jul 2026 | Week 5 | 2 | Pending
7 | Prototype Development | In-processing techniques | 14 Jul 2026 | Week 6 | 2 | Pending
8 | Prototype Development | Postprocessing techniques | 21 Jul 2026 | Week 7 | 1 | Pending
9 | Experimentation | UCI Adult Income dataset experiments | 21 Jul 2026 | Week 7 | 3 | Pending
10 | Experimentation | COMPAS dataset experiments | 28 Jul 2026 | Week 8 | 2 | Pending
11 | Analysis and Evaluation | Statistical analysis | 04 Aug 2026 | Week 9 | 2 | Pending
12 | Analysis and Evaluation | Fairness metric comparison | 11 Aug 2026 | Week 10 | 2 | Pending
13 | Analysis and Evaluation | Results visualisation | 11 Aug 2026 | Week 10 | 1 | Pending
14 | Dissertation Writing | Chapter 3: Methodology | 28 Jul 2026 | Week 8 | 2 | Pending
15 | Dissertation Writing | Chapter 4: Implementation | 04 Aug 2026 | Week 9 | 2 | Pending
16 | Dissertation Writing | Chapter 5: Results and Analysis | 11 Aug 2026 | Week 10 | 2 | Pending
17 | Dissertation Writing | Chapter 6 and 7: Discussion/Conclusion | 18 Aug 2026 | Week 11 | 2 | Pending
18 | Dissertation Writing | Chapter 1: Introduction | 25 Aug 2026 | Week 12 | 1 | Pending
19 | Finalisation | Proofreading and revision | 01 Sep 2026 | Week 13 | 1 | Pending
20 | Finalisation | Final formatting | 01 Sep 2026 | Week 13 | 1 | Pending
21 | Finalisation | Submission (23:59 deadline) | 08 Sep 2026 | Week 14 | 1 | Pending